## Risk Register
Draft Strategic Risk Register Version 4 Appendix
2006 / 2007
Strategic Risks |  | Executive
Date |  | 2006-02-09
|  |  |  | Gross Rating |  |  |  | Net Rating
No | Risk | Cause / Trigger | Consequences | Likely-hood | Impact | Score | Controls | Likely-hood | Impact | Score | Owner
1 External Influences
1.1 | Economic Increased unemployment & Benefit Claims | Downturn in Economy/ Recession Increased demand on Council Services | Increased unemployment Increased Nos on benefit Reduced income to the Council Financial | 3 | 3 | 9 | Economic Development Strategy Community Strategy Social Inclusion | 3 | 3 | 9 | Head of Policy & Performance + Cllr Anthony Stansfeld
1.2 | Inability to Recruit High Inflation Increased commuting | Overheating Economy | House price inflation Skills shortages Wage inflation Inward Commuting | 1 | 3 | 3 | Community Strategy Local Development Forum Housing Strategy Various regional strategies Local transport plan Lobbying regionally / nationally | 1 | 3 | 3 | Head of Policy & Performance + Cllr Anthony Stansfeld
1.3 | Social Civil Unrest | Unfavorable perceptions of Crime & Disorder issues | Civil unrest Perceptions / High fear of crime | 1 | 3 | 3 | Effective Community Safety Strategy Effective interagency working Appropriate funding | 1 | 2 | 2 | Chief Executive + Police Super + Cllr Emma Webster
1.4 | Terrorist Action | Action taken by international / local groups | Significant disruption Fatalities / Injuries Reputation > No Insurance against Terrorist Action | 2 | 3 | 6 | Emergency Plan / Plan tested Interagency working | 2 | 2 | 4 | HOS Public Protection + Cllr Geoff Findlay
1.5 | Environmental Major environmental incident | Major disaster Contamination Severe weather Outbreaks of disease Flooding | Significant disruption Fatalities / Injuries Reputation | 3 | 4 | 12 | Major Incident Plan | 3 | 3 | 9 | HOS Public Protection + Cllr Geoff Findlay
1.6 | Flu Pandemic | Spread flu Lack of NHS Vaccines | Significant disruption Fatalities / Injuries Reputation | 3 | 4 | 12 | Immunisation BCP | 3 | 4 | 12 | Corp Director CC&H + Cllr Geoff Findlay
1.7 | Political Intervention by Central Government or Other Regulatory Body | Statutory obligations not met Change of CPA Methodology | Legal challenge Government Intervention Compensation Poor CPA Scores Poor Audit Commission Reports | 3 | 3 | 9 | Community Plan Corporate Plan Effective Performance Management MTFS District Profile Consultation Strategy | 2 | 2 | 4 | Chief Executive + Cllr Graham Jones
1.8 | Failure to achieve good CPA Rating / JAR 07 | Statutory obligations not met Change of CPA Methodology | Legal challenge Government Intervention Compensation Poor CPA Scores Poor Audit Commission Reports | 3 | 3 | 9 | Statement of Internal Control Reports from Ext regulatory bodies Stronger Gov Project Plan | 2 | 2 | 4 | Chief Executive + Cllr Graham Jones
1.9 | Administrative Area changed / WBC absorbed into another authority | Problems arising from Local Government reorganisation | Possibility of merger with another authority | 1 | 3 | 3 | None, But Lobbying where appropriate | 1 | 3 | 3 | Chief Executive + Cllr Graham Jones
2 Corporate Management
2.1 | Strategy Non Delivery of Corporate Plan | Failure to see demographic and other external changes Failure to understand organisational context Poor / weak leadership | Ineffective forward planning Inappropriate service delivery Intervention Budget difficulties Poor CPA Scores Poor Audit Commission Reports | 3 | 4 | 12 | Community Plan Corporate Plan Effective Performance Management MTFS District Profile Consultation Strategy | 1 | 3 | 3 | Chief Executive + Cllr Graham Jones
2.2 | Inappropriate change management | Inappropriate pace of change Expectations not realised | Failure to realise opportunities CPA Intervention Inefficiency Poor reputation Capacity issues | 3 | 3 | 9 | Effective Programme management Clear Vision Effective risk management | 1 | 2 | 2 | Chief Executive + Cllr Graham Jones
2.3 | Finance Failure to adhere to financial rules of procedure | Failure to undertake appropriate Financial Planning Failure to account for unaccepted items | Qualification on the accounts Failure to set standards Reputation CPA Unacceptable under / Overspends Section 151 officer / DA Reports | 2 | 4 | 8 | MTFS including allowance for contingencies Budget monitoring Financial rules of procedure Stronger Governance Project Action Plan | 1 | 3 | 3 | Section 151 + Cllr Laszlo Zverko
2.4a | Difficulty in attracting funding | Difficult financial environment Poor management | Unable to meet objectives Limited Service Delivery Lack of Resources | 4 | 3 | 12 | MTFS External Funding Gov Lobbying Service Planning | 3 | 2 | 6 | Section 151 + Cllr Laszlo Zverko
2.4b | Loss of RSG | Changes in Government methodology | Lack of resources impacting on service delivery | 3 | 3 | 9 | Lobbying | 3 | 2 | 6 | Section 151 + Cllr Laszlo Zverko
2.4c | Loss of Specific grants | Changes in Gov priorities | Lack of resources impacting on service delivery | 3 | 2 | 6 | Budget Provision within Risk Fund | 3 | 1 | 3 | Section 151 + Cllr Laszlo Zverko
2.4d | Insufficient budget to fund Concessionary Fares | New Govt Policy | Lack of resources impacting on service delivery | 3 | 3 | 9 | Budget Provision within Risk Fund | 3 | 1 | 3 | CD E&PP + Cllr Keith Chopping
2.4e | Income targets not met | Supply / Demand Over estimate target | Lack of resources impacting on service delivery | 2 | 2 | 4 | Knowledge of the market Robust budget preparation | 1 | 3 | 3 | Section 151 + Cllr Laszlo Zverko
2.5 | Gershon targets Missed | Poor management Inability to find efficiencies | Potential for Government penalty Adverse Management Letter | 3 | 3 | 9 | Gershon Group Management Action | 2 | 2 | 4 | Section 151 + Cllr Laszlo Zverko
2.6 | HR Inability to recruit & retain to key posts | Local labour market Council/s reputation | Increased costs Lack of service continuity Inefficiency Service delivery problems | 3 | 3 | 9 | HR Policies / Management Service Continuity Performance Management Effective HR Adequate Job descriptions Service Continuity Plans Budget provision 2006/07 | 2 | 2 | 4 | Head of HR + Cllr Anthony Stansfeld
2.7 | Injury to staff working alone Security of staff | Lack of appropriate risk assessments / supervision | Fatality / Injury Financial / Insurance claims Theft / Damage Reputation | 3 | 3 | 9 | Lone working policy Risk Assessment Protection of Buildings JCC (Risk) | 2 | 2 | 4 | Head of HR + Cllr Anthony Stansfeld
2.8 | Failure to Manage PR | Poor Service or outcomes resulting in bad reports in the press / media etc | Poor Reputation CPA Low satisfaction | 2 | 3 | 6 | Effective Public / Media relations Communication Resourcing Effective Performance management framework to ensure that we get it right first time | 2 | 2 | 4 | Head of Info Comm + Cllr Anthony Stansfeld
3 Corporate Governance
3.1 | Inappropriate conduct by Staff / Members | Lack of Code of Conduct CRB Check failures | Reputation Legal Action Fatality / Injury | 3 | 3 | 9 | Code of conduct Sound Recruitment & Retention CRB Checks | 1 | 3 | 3 | Chief Executive + Cllr Graham Jones
3.2 | Poor / Inappropriate Decisions | Lack of full information for decision making | Legal Challenge Compensation Reputation | 3 | 3 | 9 | Effective Governance arrangements Including sound constitution Finance & Governance Group | 2 | 2 | 4 | Head of Policy + Cllr Anthony Stansfeld
3.3 | Service Delivery Failure | Poor / Weak management by Officers | Inefficiency Poor Reputation | 3 | 3 | 9 | Corporate Governance arrangements Management Dev. Training | 1 | 2 | 2 | Chief Executive + Cllr Graham Jones
3.4 | Poor Scrutiny | Lack of resources lack of Member engagement | Inferior decisions Regulations Poor reputation | 3 | 3 | 9 | Training Work programme Alignment with the Executive work programme Proper regulation | 2 | 2 | 4 | Chief Executive + Cllr Graham Jones
3.5 | Poor Corporate Governance | Poor policies and procedures | Legal Action Poor Reputation Reduced efficiency Intervention | 3 | 3 | 9 | Constitution Codes of Conduct Protocol Statement of Internal Control Strategic Gov Project Plan Governance & Audit Committee | 2 | 2 | 4 | Monitoring Officer + Chair of Standards Cttee
3.6 | Ineffective Business Continuity Planning | Poor service planning Lack of BCP | Service delivery fails Impact on performance | 2 | 4 | 8 | BCP process underway | 2 | 3 | 6 | Head of Assurance + Cllr Anthony Stansfeld
3.7 | Customers Stakeholders High levels of customer dissatisfaction | Inadequate Customer contact / regime | Complaints Poor reputation | 3 | 3 | 9 | Customer charter Training Clear standards | 1 | 2 | 2 | HOS + Cllr Anthony Stansfeld
3.8 | Lack of Consultation | Lack of Strategy Poor forward planning | Disengaged community | 3 | 2 | 6 | Consultation strategy framework Dedicated resources Communication Strategy Member Development | 1 | 2 | 2 | Head of Policy + Cllr Graham Jones
3.9 | Health & Safety | Failure to comply with Health & Safety Legislation | Legal / Insurance Insurance / Financial Reputation Corporate manslaughter | 3 | 3 | 9 | Effective School Service - needs analysis / risk register | 2 | 2 | 4 | Head of Assurance + Cllr Anthony Stansfeld
4 Technology
4.1 | Failure of technology | Failure of IT HR / Client systems | Service delivery / failures | 2 | 3 | 6 | Some BCP in place - further assurance required ICT Strategy Effective performance management Investment Resources | 1 | 2 | 2 | Head of ICT + Cllr Emma Webster
4.2 | Failure to meet IEG | Failure to set out plans and take IEG forward | Service delivery / failures & reduced access to services Reputation Loss of resources | 2 | 2 | 4 | IEG Government Programme ICT Strategy Capital Resources | 1 | 2 | 2 | Head of ICT + Cllr Emma Webster
4.3 | Failing to invest in technology | Investing in wrong Technology Failing to invest | Lost Resources Ineffective service delivery Service failure Lack of computability | 2 | 3 | 6 | Service Investment Programme ICT Strategy ICT Strategy Board | 1 | 1 | 1 | Head of ICT + Cllr Emma Webster
4.4 | Failure to achieve value | Implementation of IT Systems | Capacity / Resource issues | 3 | 3 | 9 | Change management | 2 | 2 | 4 | Head of ICT + Cllr Emma Webster
4.5 | Virus / Hacking Other IT security issues | Attack on Council's computer systems | Service Delivery / Failure Data Protection Reputation | 3 | 3 | 9 | Firewall / Anti Virus ITC Policy | 2 | 3 | 6 | Head of ICT + Cllr Emma Webster
5 Service Delivery / Procurement
5.1 | Failure to meet objectives No clear targets / objectives | Weak performance management | Reputation Potential Intervention Poor CPA Scores Ineffective Service Delivery | 3 | 3 | 9 | Service Planning Performance management Systems Effective Resource Planning | 2 | 2 | 4 | Head of Policy + Cllr Graham Jones
5.2 | Poor / Ineffective procurement | Poor Governance Lack of Skills | Waste / Inefficiency | 3 | 3 | 9 | Procurement Strategy Efficient Processes | 3 | 2 | 6 | Section 151 + Cllr Anthony Stansfeld
6 Failure to Deliver / Manage Major Projects
6.1 | Shaw House | Poor Project Management Economic | Delay / Overspend Reputation Project collapse Insurance | 3 | 3 | 9 | Effective project Plan Regular Resource Monitoring | 2 | 2 | 4 | Project sponsor + Cllr Marcus Franks
6.2 | Park Way | Poor Project Management | Delay / Overspend Reputation Project collapse | 3 | 2 | 6 | Effective project Plan Regular Resource Monitoring | 2 | 2 | 4 | Project sponsor + Cllr Emma Webster
6.3 | Market St | Poor Project Management | Delay / Overspend Reputation Project collapse | 3 | 2 | 6 | Effective project Plan Regular Resource Monitoring | 2 | 2 | 4 | Project sponsor + Cllr Emma Webster
6.4 | Newtown Resource Centre | Poor Project Management | Delay / Overspend Reputation Project collapse Impact on Service Vulnerable | 3 | 3 | 9 | Effective project Plan Regular Resource Monitoring | 2 | 2 | 4 | Project sponsor + Cllr Joe Mooney
6.5 | Waste PFI | Poor Project Management Only ONE Bid Received Political Issues Affordability | Delay / Overspend Reputation Project collapse | 4 | 4 | 16 | Effective project Plan Regular Monitoring Preferred bidder negotiations | 4 | 3 | 12 | Project sponsor + Cllr Geoff Findlay
6.6 | Denefield | Failure to deliver 1. Financial 2. Project Planning 3. Continued Operation of schools | Reputation Political Issues on National and Local basis | 4 | 4 | 16 | Effective project management process | 3 | 2 | 6 | HOS Education + Cllr Graham Pask
6.7a | Planning Related Kennet Valley Park | Failure in planning process | Impact on Council / Education & transport facilities Government intervention | 4 | 4 | 16 | Consultation / robust planning process | 2 | 4 | 8 | HOS PTS + Cllr Keith Chopping
6.7b | IMF, Aldermaston | Legal / management process failure | Governement intervention | 3 | 2 | 6 | Consultation / robust management process | 2 | 2 | 4 | HOS PTS + Cllr Keith Chopping
6.7c | AWE Redevelopment | Failure in Planning process | Public order Government Intervention | 4 | 3 | 12 | Consultation / robust planning process | 4 | 2 | 8 | HOS PTS + Cllr Keith Chopping
7 | Failure to Deliver Partnerships
7.1 | Service Delivery Strategic Partners | Risks associated with the failure of partnerships Health reorganisation | Partnership failure Progress limited Service delivery | 3 | 3 | 9 | Health Partnership Working Party Joint strategic Panel | 2 | 2 | 4 | CD CC&H + Cllr Joe Mooney
7.2 | Under achievement of PSA (1) | Poor Management Unachievable targets | Reduced reward Reduced outcomes in local community Reputation Failure to meet targets Potential Financial Implications | 3 | 3 | 9 | Effective Performance Management Remedial Action | 2 | 3 | 6 | Head of Pol & Perf + Cllr Anthony Stansfeld
7.3 | Underachievement of Local Strategic Partnership (LSP) LAA / PSA 2 | Poor Management Unachievable targets | Reduced reward Reduced outcomes in local community Reputation Failure to meet targets Potential Financial Implications | 3 | 3 | 9 | Effective Performance Management Remedial Action | 2 | 2 | 4 | CD CC&H + Cllr Joe Mooney + Cllr Graham Jones
7.4 | Under achievement of Safer Communities Partnership | Poor Management Unachievable targets | Reduced reward Reduced outcomes in local community Reputation Failure to meet targets Potential Financial Implications | 3 | 3 | 9 | Effective Performance Management Remedial Action | 2 | 2 | 4 | CE + Cllr Geoff Findlay / Cllr Emma Webster
7.5 | Under achievement of Children's Trust | Poor Management Unachievable targets | Reduced reward Reduced outcomes in local community Reputation Failure to meet targets Potential Financial Implications | 3 | 3 | 9 | Effective Performance Management Remedial Action | 2 | 2 | 4 | CD CC&H + Cllr Graham Pask
7.6 | Under achievement of Health & Well being Partnership | Poor Management Unachievable targets | Reduced reward Reduced outcomes in local community Reputation Failure to meet targets Potential Financial Implications | 3 | 3 | 9 | Effective Performance Management Remedial Action | 2 | 2 | 4 | CD CC&H + Cllr Joe Mooney
Managed out of Business
7.1 | Amey Partnership ( CB key Risk ) | Failure / Financial or Business strategy | Service delivery Reputation Potential Default |  |  |  | Effective contract management Good working relationship between both parties Managed / Negotiated return
2.2 | Planning Service ( CB Key Risk ) | Government Intervention in the Planning Department | Loss of democratic control Loss of budgetary control |  |  |  | Adequate management / staffing Effective performance management Improvement Action plan

## Action Plan
Strategic Risk Action Plan Red Risks Appendix B
Owner |  | The Executive
Date |  | 2006-02-09
CB Key Risks
Risk No | Area of Concern / Risk Scenario | Existing Controls | Gross Risk Score | Net Risk Score | Required Controls or Action | Responsibility of | Budget Constraint | Target Date
1.1 | Economic Increased unemployment & Benefit Claims | Economic Development Strategy Community Strategy Social Inclusion | 9 | 9 | None Possible | Nick Carter | None | Not Applicable
1.5 | Environmental Major disaster Contamination Severe weather Outbreaks of disease Flooding | Major Incident Plan | 12 | 9 | Regular review / Intelligence and testing | John Parfitt | None | On-Going
1.6 | Flu Pandemic | Immunisation BCP | 12 | 12 | Regular consultation WBC Flu Group Various multi agency groups | Margaret Goldie | None | On - Going
6.5 | Major Projects Waste PFI | Effective project Plan Regular Monitoring Preferred bidder negotiations | 16 | 12 | Sites and Planning Ensure affordability | Bill Jennison |  | On - Going
6.7a | Kennet Valley Project | Consultation / robust planning process | 16 | 8 | Tight monitoring and supervision | Tim Slaney
6.7c | AWE Redevelopment | Consultation / robust planning process | 12 | 8 | Tight monitoring and supervision | Tim Slaney